## Read me
Chillibyte website project trackers
One workbook per project. Duplicate it, rename it, delete the tabs the project does not need.
The spec builder tells you which tabs this project needs — and which it does not.
Row 3 on every tab is the header. Row 4 is a greyed worked example — delete it or type over it.
Status columns have dropdowns. Panes are frozen and filters are on.
TABS
Gate tracker The spine. One row per gate. Start here.
Estimate baseline NEW. The number every later change is measured against.
Decision log Why something was chosen. Protects reasoning.
Change log What moved after approval. Protects scope.
Variation register NEW. What the change was worth. Protects revenue.
Sitemap Pages, URLs, purpose, approval status.
Page inventory The same pages as a work plan.
Content matrix Every content item, with an owner AND a deadline.
Block inventory Reuse / adapt / build new. Controls development scope.
Risks & assumptions With owners and mitigations.
QA Tested against the agreed support matrix, not against everything.
Launch Pre- and post-launch checklist.
THE THREE RECORDS PEOPLE CONFUSE
Decision log — why we chose something. Stops the same argument happening three times.
Change log — what changed after approval, and its impact.
Variation — what that change is worth, agreed with the client BEFORE the work happens.
A change log without a variation register just documents unpaid work politely.
You can still choose to absorb something. The process does not require charging for
everything — it requires the decision to be visible.

## Gate tracker
Gate tracker
The spine of the project. Approval names artefacts AND their version — otherwise there is nothing to point at later.
Approval | Name | Route | Required artefacts (with version) | Owner | Approver | Basecamp ticket | Status | Sent for approval | Approved date | Days taken | Within SLA? | Decision log refs | Change log refs | Notes
Studio brief | Studio brief accepted | All | Studio brief v1.0 | Sales | Head of Web | Approval: studio brief | Complete | 14/04 | 15/04 | 1 | Yes |  |  | Configurator excluded — phase 2 candidate

## Estimate baseline
Estimate baseline [NEW]
Set at the discovery approval, re-baselined at the build specification approval, actuals recorded at the project closure approval. Without this, scope creep cannot be demonstrated — only asserted.
Phase | Step | Discovery baseline (hrs) | Build spec re-baseline (hrs) | Actual (hrs) | Variance | Variance % | Of which billed as variation | Why it varied
Structure | Block identification | 4 | 4 | 5 | +1 | 25% | 0 | One extra block found during outlining

## Decision log
Decision log
Why something was chosen. Protects reasoning — and lets someone new understand the project without asking anyone.
Decision ID | Date | Project phase | Decision title | Context | Options considered | Selected decision | Rationale | Impact | Reversal cost | Owner | Approver | Approval source | Status | Related artefacts | Notes
DEC-001 |  | Discovery | Project route selected | Discovery indicates likely complexity | Light; standard; full | Standard | Default route for modular B2B service sites | Sets artefact depth and gate count | Medium | Head of Web | Internal | Approval: discovery ticket | Proposed | Discovery summary

## Change log
Change log
What moved after approval. The last five columns are new: a change process that cannot raise a charge just converts scope creep into unpaid work more politely.
Change ID | Date raised | Raised by | Description | Related approved item | Classification | Reason | Impact area | Impact detail | Effort (hrs) | Chargeable? | Variation ref | Decision | Client approved | Basecamp reference | Status | Completed date | Notes
CHG-001 |  | Client | Add new page after sitemap approval | Sitemap v1.0 | New scope | New stakeholder request | Structure / content / build | New URL, navigation, copy and possible template work | 6 | Yes | VAR-001 | Accepted | Yes |  | Open

## Variation register
Variation register [NEW]
What each accepted change was worth. This tab is the difference between recording scope creep and being paid for it.
Variation ref | Date | Change log ref | Description | Effort (hrs) | Rate | Value | Offered as | Client decision | Decision date | Schedule impact (days) | Invoiced? | Notes
VAR-001 |  | CHG-001 | Additional service line page and template variant | 6 | £86.67 | £520 | Proceed now / defer / decline | Accepted |  | 2 | No | Baseline updated

## Sitemap
Sitemap
Approved at the sitemap approval. Where there is an existing site, every old URL maps to a new one or to a documented retirement.
Page | Proposed URL | Parent | Purpose | Primary audience | Primary CTA | Secondary CTA | Template type | Navigation placement | SEO priority | Old URL | Redirect type | Content owner | Approval status | Notes
Home | / | n/a | Introduce business and route users | All audiences | Enquire | View services | Unique | Main nav | High | / | — | Copywriter / client | Draft

## Page inventory
Page inventory
The same pages as a work plan. Template count drives effort far more than page count does.
Page | URL | Page type | Unique or repeatable | Primary job | Audience | Content status | Design status | Build status | Template / block pattern | Media required | Owner | Approval status | Notes
Home | / | Landing | Unique | Set proposition and route users | All | Not started | Not started | Not started | Home pattern | Hero image / service imagery | Head of Web | Draft

## Content matrix
Content matrix
Every content item has an owner AND a deadline. Late client content is the most common cause of website overrun — the deadline column is the fix.
Page | Section | Content needed | Approx. length | Content owner | Source | Deadline | Days late | Escalated? | Media needed | Media owner | Status | Dependency | Notes
Home | Hero | Headline, intro, CTA text | 30–60 words | Copywriter | Discovery summary |  |  | No | Hero image | Client | Not started | Style direction

## Block inventory
Block inventory
Approved at the block inventory approval. Collapse duplicates hard — if this list is as long as your section list, no consolidation has happened.
Block | Used on | Status | Reuse decision | Purpose | Fields | Design needed | Responsive notes | PHP structure | field group | Base SCSS | Theme SCSS | Design library entry | Build impact | Assigned to | Est. hrs | Actual hrs | Handed back | Approval status | Notes
Hero | Home, landing pages | Existing / adapt | Adapt existing | Introduce page and direct action | Heading, intro, image, buttons | Yes | Mobile image crop needs checking | Reusable block PHP | Hero group | Core layout | Project styling | Yes | Medium | Web Developer | 5 |  | No | Draft

## Risks & assumptions
Risks and assumptions
Every entry needs an owner and a validation route. A risk with no owner is a wish.
ID | Type | Date | Description | Impact if realised | Likelihood | Impact | Owner | Mitigation / validation | Status | Related decision | Notes
RA-001 | Assumption |  | Client will supply usable photography | Design quality and launch timing affected | Medium | Medium | Account Management | Confirm asset availability during discovery | Open

## QA
QA checklist
Tested against the support matrix and accessibility target agreed at the discovery approval — and nothing beyond them. That is what makes QA finishable.
Category | Check | Owner | Status | Issue | Severity | Fix required | Retested | Basecamp reference | Notes
Structure | Sitemap matches approved structure |  | Not started
Navigation | Main navigation works across the support matrix |  | Not started
Navigation | Subnav and breadcrumbs correct |  | Not started
Content | No placeholder or dummy content remains |  | Not started
Content | Headings match the approved page outlines |  | Not started
Forms | Every form submits AND arrives at the correct destination |  | Not started
Forms | Validation and error states work |  | Not started
Responsive | Key pages checked at every breakpoint in the support matrix |  | Not started
Responsive | Checked on every browser in the support matrix — and nothing beyond it |  | Not started
Accessibility | Heading order is sequential, no skipped levels |  | Not started
Accessibility | All text meets the contrast target |  | Not started
Accessibility | Focus states visible on every interactive element |  | Not started
Accessibility | Keyboard navigation reaches everything, including scroll regions |  | Not started
Accessibility | Images have meaningful alt text |  | Not started
Performance | Images optimised and correctly sized |  | Not started
Performance | Core Web Vitals checked on the heaviest pages |  | Not started
SEO | Titles and meta descriptions present and unique |  | Not started
SEO | Indexability correct — staging noindex removed |  | Not started
SEO | XML sitemap generated and correct |  | Not started
Redirects | Every old URL tested against the current-state audit list |  | Not started
Redirects | PDF and asset paths preserved or redirected |  | Not started
Compliance | Cookie consent actually gates non-essential cookies |  | Not started
Compliance | Privacy policy describes the site as built |  | Not started
Compliance | Form data destination and retention documented |  | Not started
Analytics | Analytics firing and consent mode configured |  | Not started

## Launch
Launch checklist
Most launch problems are something not prepared or something not tested. Preparation is the entire job.
Category | Task | Owner | Status | Dependency | Issue | Severity | Basecamp reference | Notes
Pre-launch | Final client approval captured |  | Not started | Staging approval
Pre-launch | Content freeze declared and confirmed to the client |  | Not started | Staging approval
Pre-launch | Full backup taken AND restore verified |  | Not started | Hosting access
Pre-launch | Redirects implemented and tested against the audit URL list |  | Not started | Current-state audit
Pre-launch | DNS access confirmed and TTL reduced |  | Not started | DNS credentials
Pre-launch | Hosting environment provisioned and tested |  | Not started
Pre-launch | Integrations moved from sandbox to production |  | Not started | Credentials
Pre-launch | Compliance cleared — consent, privacy, retention |  | Not started | Compliance approval
Pre-launch | Rollback plan written and read by whoever is launching |  | Not started
Pre-launch | Launch window scheduled in working hours, not a Friday |  | Not started
Pre-launch | Warranty window agreed with the client IN WRITING |  | Not started | Launch approval
Launch | Deploy to production |  | Not started | Launch approval
Launch | DNS switched |  | Not started
Post-launch | Live smoke test — all key journeys walked |  | Not started | DNS propagated
Post-launch | Every form submitted with real data and confirmed arriving |  | Not started
Post-launch | Analytics and Search Console verified firing |  | Not started
Post-launch | Sitemap submitted; crawl errors monitored for one week |  | Not started
Post-launch | Redirects spot-checked live |  | Not started
Post-launch | Client notified and handover notes delivered |  | Not started
Post-launch | Warranty start date recorded |  | Not started
Post-launch | Estimate variance recorded on the Estimate baseline tab |  | Not started
Post-launch | Reusable blocks committed to the library |  | Not started
Post-launch | Retrospective held — each action with an owner and a date |  | Not started
Post-launch | Care plan conversation held while goodwill is high |  | Not started